# Board Presentation Deck Outline

Living Water Network Inc.

Table of Contents

# BOARD PRESENTATION DECK

## Alignment Meeting — 2026–2027 Launch Posture

Purpose: align the seven-member board on positioning, launch plan, roles, and fundraising commitments so the November 2026 gala and first cohort launch can proceed with unified leadership.

Recommended format. 11 slides. 30–45 minute meeting. 20 minutes of structured discussion. Clear decisions captured in minutes. Pre-reads sent seven days ahead.

## Deck Structure

### Slide 1 — Why We Are Here Tonight

Finalize the launch posture of Living Water Network for fiscal year 2026–2027.

### Slide 2 — Strategic Clarity

LWN is not a training org. LWN is not a missions org. LWN is a formation movement that produces sent leaders.

### Slide 3 — Organizational Identity

Mission, vision, values. Core model: Formation → Activation → Deployment.

### Slide 4 — Where We Are Today

Incorporated. EIN secured. Bylaws governance. Curriculum complete. Cohort model built. Ecuador partnership secured.

### Slide 5 — Launch Timeline

Six-month plan from alignment through gala execution in November 2026, and deployment in Q1 2027.

### Slide 6 — Roles & Responsibilities

Core operating team chart. Board expectations: give, get, or open doors.

### Slide 7 — Financial Picture

Revenue streams. Year One target: $145K. Sponsor strategy. Monthly donor math (150 × $100 = $180K).

### Slide 8 — Fundraising Expectations (Board)

Each board member: a defined annual personal commitment, three qualified introductions, one gala table hosted.

### Slide 9 — Key Risks

Execution capacity. Board engagement depth. Sponsor pipeline depth. Program delivery quality in Year One.

### Slide 10 — Decisions Needed Tonight

Approve positioning statement. Approve gala date and theme. Approve core team hires. Commit individual board give/get goals in writing.

### Slide 11 — What Comes Next

Sponsor outreach window opens. First cohort launch date confirmed. Gala date locked. Quarterly board check-in scheduled.

## Pre-Read Packet (Send 7 Days Before Meeting)

- Business Plan (current)

- Year One Budget draft

- Fundraising Strategy Plan

- Role Descriptions & SOP Framework

- Board Commitment Letter (for signature)

- Prior meeting minutes

## Key Decisions to Capture in Minutes

- Approval of the formal positioning statement as the organization’s public identity.

- Approval of gala date, venue, and theme.

- Approval of operating team hires and compensation framework.

- Individual board giving and fundraising commitments recorded in writing.

- Ratification of the 12-month roadmap and Year One financial plan.

## Board Member Individual Ask

Before leaving the meeting, each board member signs a one-page commitment letter specifying:

- Personal annual giving amount (minimum to be set by the board).

- Three named introductions (by month/quarter).

- Willingness to host or co-host one gala table.

- Committee assignment (Development, Programs, Missions, Governance, or Finance).

- Commitment to attend four quarterly meetings and the annual retreat.

## Meeting Run-of-Show (45 Minutes)

- 0:00 — Opening / Prayer (3 min). Founder.

- 0:03 — Strategic Clarity (5 min). Slides 1–3.

- 0:08 — State of the Movement (7 min). Slides 4–5.

- 0:15 — Roles & Finance (8 min). Slides 6–7.

- 0:23 — Board Expectations (5 min). Slide 8.

- 0:28 — Risks & Decisions (10 min). Slides 9–10. Structured discussion.

- 0:38 — Next Steps & Sign (5 min). Slide 11. Sign commitment letters.

- 0:43 — Close / Prayer (2 min).