# Execution Guide & Action Plan

Living Water Network Inc. — Your Operating Playbook

Table of Contents

# EXECUTION GUIDE & ACTION PLAN

## How to take this launch suite from document to movement

This is the master guide that keeps the other documents alive. Read this first. Revisit it weekly. Everything else is reference — this is operating discipline.

## How to Use This Launch Suite

Each document in the suite has a purpose, an audience, and a moment of use. Do not try to read them all in one sitting.

| Document | Primary Use | Who Owns It |
| --- | --- | --- |
| 01 · Business Plan | Single source of truth for strategy, metrics, and roadmap. | Founder |
| 02 · Gala Pitch Deck Outline | Brief the designer and emcee. Build the deck from this. | Development Lead |
| 03 · Donor Scripts & Messaging | Speaking, writing, training anyone who represents LWN. | Founder + Development Lead |
| 04 · Board Presentation Deck | Quarterly alignment with the board. | Founder |
| 05 · Roles & SOP Framework | Hiring, onboarding, role clarity, weekly accountability. | Operations Lead |
| 06 · Fundraising Strategy | Daily/weekly fundraising execution. | Development Lead |
| 07 · Website Copy Rewrite | Hand to designer/developer for site refresh. | Marketing Lead |
| 08 · Vision Document | Share externally. Print as PDF. Use with church partners and major donors. | Founder |
| 09 · Execution Guide (this document) | Operating discipline. Weekly and monthly review. | Operations Lead |
| 10 · Year One Budget | Financial planning and monthly finance review. | Operations Lead |
| 11 · Launch Readiness Checklist | Gate every phase. Nothing ships without this being green. | Operations Lead |

Read-first order for a new team member. Vision Document → Business Plan → Roles & SOPs → relevant function doc → this Execution Guide.

## The Six-Phase Launch Plan

Phases align with the business plan roadmap. Every phase has a gate — specific evidence required before moving to the next phase. Do not advance on calendar alone.

### Phase 1 — Clarity & Alignment (Now → End of May 2026)

Outcomes. Positioning locked. Board formed and committed. Core team assigned. Budget approved. Quiet-phase donor conversations begun.

Gate to Phase 2. Positioning statement formally adopted by board vote. Board commitment letters signed. First operating budget approved. CRM selected.

### Phase 2 — Foundation Build (June → July 2026)

Outcomes. First cohort launched or calendared. Testimony capture engine running. Gala concept locked. Sponsor prospect list built (minimum 20 qualified prospects).

Gate to Phase 3. Cohort curriculum approved and enrollment open. Gala date, venue, and theme locked. Sponsor prospect list in CRM with assigned owners.

### Phase 3 — Momentum (August → September 2026)

Outcomes. Title sponsor secured. Gala marketing live. Local activation events running. Ecuador trip logistics in motion.

Gate to Phase 4. Title sponsor agreement signed. Public gala page live. 30% of monthly-donor target secured in quiet phase.

### Phase 4 — Scale (October → November 2026)

Outcomes. Full gala attendance push. Pledge pipeline loaded. All day-of logistics locked. Vision video produced.

Gate to Phase 5. 150+ confirmed RSVPs. Run-of-show signed off. Vision video final cut approved.

### Phase 5 — Gala Execution (November 2026)

Outcomes. Gala delivered. Funds committed. Monthly donors onboarded. Media captured.

Gate to Phase 6. Post-gala conversion complete within 14 days. Thank-yous sent. Pledge payments confirmed.

### Phase 6 — Deployment (December 2026 → March 2027)

Outcomes. Second cohort launched. First Ecuador trip executed. Year One wrap report published. Year Two planning complete.

## 90-Day Action Plan (April 24 → July 24, 2026)

Task format: [Workstream] Action · DRI · Due Date. Adjust DRIs based on who holds each role. Until roles are filled, founder holds by default.

### Weeks 1–2 (Apr 24 – May 8)

- [Governance] Convene board for alignment meeting using Document 04. · Founder · May 8

- [Governance] Collect signed board commitment letters. · Founder · May 8

- [Strategy] Formally adopt defining statement and values. · Board vote · May 8

- [Legal] Confirm current standing with Georgia Secretary of State. Schedule any annual filings. · Operations · May 1

- [Legal] Verify 501(c)(3) determination letter is on file and insurance is current. · Operations · May 8

- [Finance] Approve Year One budget (Document 10). · Board · May 8

- [Finance] Open dedicated operating account and set up bookkeeping (QuickBooks Online or Aplos). · Operations · May 8

- [Development] Build initial prospect list of 50 major-donor and sponsor candidates. · Founder + Development · May 15

- [Marketing] Audit current website for accuracy against new positioning. Document changes. · Marketing · May 8

### Weeks 3–4 (May 9 – May 22)

- [Operations] Select CRM and begin data migration. · Operations + Development · May 22

- [Operations] Select email marketing tool (MailerLite, Flodesk, or Mailchimp). · Marketing · May 22

- [Operations] Stand up shared Google Workspace / Drive folder structure. · Operations · May 15

- [Development] Begin quiet-phase major-donor coffees. Target: 10 in 30 days. · Founder · Ongoing

- [Programs] Finalize first cohort calendar, location, and enrollment page. · Programs · May 22

- [Marketing] Draft new homepage, About, Programs, Give, Missions pages from Document 07. · Marketing · May 29

- [Missions] Formalize Ecuador / FHC scope of work in writing. · Missions · May 22

### Weeks 5–6 (May 23 – June 5)

- [Development] Build gala sponsor pipeline in CRM. Minimum 20 qualified prospects. · Development · June 5

- [Development] Draft sponsor proposal packet (tiered benefits + use-of-funds). · Development + Marketing · June 5

- [Programs] Open enrollment for first cohort. · Programs · May 29

- [Programs] Recruit and train facilitators. Run one practice session. · Programs · June 5

- [Marketing] Refreshed website live. · Marketing · June 5

- [Marketing] Launch email newsletter. First issue out. · Marketing · June 5

- [Finance] Monthly close process documented and executed for May. · Operations · June 5

### Weeks 7–8 (June 6 – June 19)

- [Development] Begin sponsor outreach (warm intros first). · Development + Founder · Ongoing

- [Programs] First cohort launches. · Programs · Week of June 15

- [Programs] Testimony capture protocol live. First interviews scheduled. · Programs + Marketing · Ongoing

- [Missions] Trip participant application opens. · Missions · June 19

- [Marketing] Gala landing page (private / save-the-date) published. · Marketing · June 19

### Weeks 9–10 (June 20 – July 3)

- [Development] Lock gala venue and date. · Development · June 26

- [Development] Finalize gala theme and creative direction. · Development + Marketing · July 3

- [Programs] Mid-cohort check-in and participant NPS. · Programs · Ongoing

- [Marketing] Gala brand assets package complete (logo lockups, invitation template, social templates). · Marketing · July 3

- [Finance] First quarterly board finance review. · Operations · Late June

### Weeks 11–13 (July 4 – July 24)

- [Development] Title sponsor prospect shortlist (top 5) with next-move dates. · Development + Founder · July 10

- [Development] Sponsor proposals out to top 10 prospects. · Development · July 17

- [Programs] Cohort #1 wrap planning and debrief template ready. · Programs · July 24

- [Missions] Confirm trip dates and participant commitments. · Missions · July 24

- [Marketing] Vision video production kickoff. · Marketing + Founder · July 24

- [Governance] Second board quarterly meeting scheduled. Pre-read distributed. · Founder · July 24

## Aug – Nov Plan (High Level)

- August. Title sponsor close. Vision video first cut. Gala marketing goes public. Table sponsor sales open.

- September. Cohort #1 completes. Table sales push. Ecuador trip preparation kickoff for participants. Begin monthly donor campaign.

- October. Gala RSVPs peak. Final run-of-show. Tech rehearsal booked. Speakers confirmed. Media kit ready.

- November. Gala week. Dry run. Execute gala. 14-day post-gala conversion window: pledge confirmations, thank-yous, monthly donor onboarding.

## Dec 2026 – Mar 2027 Plan (High Level)

- December. Year-end giving push. Annual report draft. Cohort #2 enrollment opens.

- January. Annual giving statements out by Jan 31. Cohort #2 launches. 990 prep starts.

- February. First Ecuador trip executes (or March, per FHC alignment).

- March. Trip debrief. Year Two planning retreat. Fiscal year summary published.

## Meeting Rhythm Reference Card

| Meeting | Cadence | Attendees | Output |
| --- | --- | --- | --- |
| Leadership Sync | Weekly, Monday 60 min | Founder, Ops, Dev, Programs, Missions, Marketing | DRI + date on every action |
| Fundraising Pipeline | Weekly, 30 min | Founder, Dev Lead | Pipeline moves documented |
| Finance + Donor Review | Monthly, last Friday | Founder, Ops, Dev | Cash position + donor status |
| Quarterly Board Meeting | Quarterly | Board + Founder + Ops | Minutes, decisions, commitments |
| Programs Check-In | Weekly during cohort | Programs + Facilitators | Participant status |
| Missions Check-In | Monthly | Missions + FHC | Trip readiness |
| Annual Planning Retreat | Q1 | Full team + Board chair | Annual plan, budget, 3-year view |

## Decision Log Template

Maintain a running Decision Log. Every non-trivial decision captured with this schema:

| Date | Decision | Context | DRI | Dissents | Review Date |
| --- | --- | --- | --- | --- | --- |

Store in shared drive. Reference by ID in all meeting minutes.

## Risk Register

Top risks monitored monthly. Status: Green / Yellow / Red. Owner accountable for mitigation progress.

| # | Risk | Likelihood | Impact | Mitigation | Owner |
| --- | --- | --- | --- | --- | --- |
| 1 | Title sponsor not secured before October | Medium | High | Multi-prospect pipeline. Early outreach. Tiered fallback underwriting plan. | Development |
| 2 | Board member disengagement | Medium | High | Signed commitment letters. Quarterly accountability. | Founder |
| 3 | Cohort quality issues in Year One | Medium | Medium | Facilitator training. Mid-cohort NPS. Iterate fast. | Programs |
| 4 | Ecuador trip safety / logistics | Low | High | Insurance. Partner vetting. Emergency protocol. Risk review pre-trip. | Missions |
| 5 | Cash flow gap pre-gala | Medium | High | Earned revenue cohorts. Major-donor quiet phase. Line of credit if needed. | Operations |
| 6 | Legal / compliance lapse | Low | High | Compliance calendar. Quarterly counsel check-in. | Operations |
| 7 | Brand / messaging drift | Medium | Medium | Single source of truth (this suite). Brand guide. Quarterly audit. | Marketing |
| 8 | Founder bandwidth overload | High | High | Role handoff plan. Contractor bench. Protected calendar. | Operations + Founder |

## Gala Day-Of Run-of-Show Template

Customize when venue and timing are confirmed. This is the structure.

T-minus 24 hours. Venue walk-through. Tech check. Vendor confirmations. Team brief.

T-minus 4 hours. Volunteer check-in. Registration setup. AV test with live speaker. Food and beverage positioning. Pledge cards placed.

T-minus 30 minutes. Volunteer huddle. Prayer. Doors check. Music cues loaded.

Arrival (60 min). Guests arrive. Photography. Welcome reception. Sponsor recognition in passing.

Program (75 min). Run 17-slide deck per Document 02. Founder ~8 minutes on stage. Financial invitation followed by 2 minutes of silent reflection and pledge response. Band / music cover during commitment moment.

Dessert & Mingle (45 min). Founder works the room. Development Lead captures verbal commitments. Volunteers sweep for pledge cards.

Close (15 min). Thank-you. Final call. Closing prayer. Exit.

T-plus 24 hours. Thank-you emails to all attendees. Pledge data into CRM. Social post with one photo and the gratitude message.

T-plus 7 days. All pledges confirmed. All monthly donors onboarded. Post-mortem scheduled.

## How to Keep This Plan Alive

- Print the first 90 days. Put it somewhere physical. Cross tasks off by hand.

- Review weekly. Leadership sync opens with: “What shipped. What slipped. What’s next.”

- Update monthly. Revise the next 90 days at month end based on what you learned.

- Reset quarterly. Board meeting anchors the reset. Re-baseline metrics. Re-score risks.

- Post-mortem every campaign. What worked. What didn’t. What we’ll change. File it.

A plan is not a promise. It is a running commitment to tell the truth about progress. Stay honest with it, and it will stay useful to you.